## Slide 1
1st Step of Structure Plan Preparation
Image Collection and Processing

## Slide 2
Sl. No . | Name of work
1 | Image Collection
2 | Processing of Image
3 | Rectification
4 | Cleaning of Image
5 | Bandwidth Colour Composition
6 | Geo Referencing of Image
Steps of Image Collection & Processing

## Slide 4
2st Step of Structure Plan Preparation
Digitization and Field Check

## Slide 5
Sl | Name of work | Sl | Name of work
7 | Prepare .shp file for Digitization With Arc GIS | 30 | Varification of Ward wise database and Map fron Municipality
8 | Physical Feature Digitization from Image | 31 | Wardwise map Prepare and Print
9 | Prepared Map from Image Digitization for Field Check and Data Collection | 32 | Para/ Neighborhood Demarcation From BBS
10 | Physical Feature Survey and Data Collection with the help of Previously Digitized map | 33 | Field Check of Para/ Neighborhood Demarcation
11 | GIS Database Prepare and Update from Collected Field Data | 34 | Reform/Correction and Update of Para/ Neighborhood Boundary
12 | Field Check By MSDP Team | 35 | Parawise Database Preparation
13 | Additional Building Data Collection By MSDP Team | 36 | Parawise Map prepare and Print
14 | Floor wise Building Data Collected from Field By MSDP Team | 37 | Varification of Para wise database and Map from Municipality
15 | GIS Database Prepare and Update By MSDP Team | 38 | Unionwise Database prepare
16 | Physical feature database | 39 | Specify Growth centers from unions and
17 | Building use Decleration | 40 | Map Prepare and Print fron Union Database
18 | Landuse database | 41 | Field check of two Union and 10 Specific Growth cener
19 | Important point Feature database | 42 | Database of Unions and Growth Centers are Corrected and Updated
20 | Road Network Database | 43 | Print Growth Center and Union Database
21 | Waterbody Database | 44 | Print Unionwise Map
22 | Drainage database | 45 | Sample Field check of Different database
23 | Embankment,Bridge, Culvert Database | 46 | Analysis of Different Database
24 | Admin boundary Demarcation | 47 | Map Preparation From Different Database and
25 | KPI Demarcation | 48 | Print Map
26 | Educational Structure demarcation |  | 
27 | Religious Facilities Demarcation |  | 
28 | Ward wise Database prepare |  | 
29 | Ward wise Database and Map Print |  | 
Steps of Digitization and Field Check

## Slide 6
Physical Feature Survey
An Example

## Slide 7
Sl No | Collected Information Type | Sl No | Collected Information Type
1 | Final__ID | 23 | NAME
2 | UDD_Name | 24 | STRUCTYPE
3 | UDD_Ward | 25 | FLOOR
4 | U_Gr_F_Us | 26 | MobileTowe
5 | U_1st_F_Us | 27 | HoldingNo
6 | U_2nd_F_Us | 28 | OccupantDa
7 | U_3rd_F_Us | 29 | OccupantNi
8 | U_4th_F_Us | 30 | OccupancyC
9 | U_5th_F_Us | 31 | StructureA
10 | U_6th_F_Us | 32 | StructureT
11 | U_7th_F_Us | 33 | HeavyOverh
12 | U_8th_F_Us | 34 | NumberApar
13 | U_9th_F_Us | 35 | SoftStory
14 | U_10_F_Us | 36 | PoundingPo
15 | U_11_F_Us | 37 | Stories
16 | U_12_F_Us | 38 | StrucShape
17 | U_Floor | 39 | Ground_Set
18 | UDD_Para | 40 | ShortColum
19 | U_Str_Typ | 41 | PhysicalCo
20 | U_Hol_Num | 42 | Struc_Slop
21 | U_House_H | 43 | Struse1T
22 | U_Con_Year | 44 | Struse2T
 |  | 45 | Struse3T
 |  | 46 | STRUSE4T
An Example

## Slide 8
An Example

## Slide 9
Water body Type | Area in Acre | %
Borrow Pits | 47.21 | 0.37
Ditch | 544.27 | 4.27
Gheer (Fish Cultivation Only) | 1496.04 | 11.74
Khal | 327.15 | 2.57
Lake | 62.31 | 0.49
Marsh Land | 3065.74 | 24.05
Pond | 4505.13 | 35.34
River | 2699.19 | 21.18
Grand Total | 12747.05 | 100.00
Waterbody Type | Total No | %
Ditch | 2070 | 8.85
Gheer (Fish Cultivation Only) | 3344 | 14.30
Pond | 17976 | 76.85
Grand Total | 23390 | 100.00
Existing Water body
An Example

## Slide 10
An Example

## Slide 11
3rd Step of
Structure Plan Preparation
Mauza Map Digitization and Layout Preparation

## Slide 12
Geo-referenced Mauza Check
GCP has been Collected in Total 58 Locations by Using RTK GPS
On Basis of these GCP Geo-referenced Mauza has been Checked
Source : GIS Database

## Slide 13
4th Step of Structure Plan Preparation
Preparation of Digital Elevation Model

## Slide 14
Sl | Name of work
93 | DTM points generated(10m interval) from 3d Image
94 | DEM Preparation
95 | Prepare Contour from DEM
96 | Collect RL from Field for DEM(RL) checking
97 | Find out Difference By using GIS Software
98 | Check Contour from Field(rl)
99 | DEM Correction and Finalization
100 | Contour Correction and Finalization
101 | Inundation Data collection
102 | Flood Map Preparation from DEM
Steps of DEM Preparation

## Slide 15
DEM

## Slide 16
DEM Check & Correction
The Circles in Red Colour Marked Different Locations Where RL has been Collected for Checking of DEM
Source : GIS Database
Total Dem Check Points 231

## Slide 17
5th Step of Structure Plan Preparation
Preparation of Drainage Map

## Slide 18
Sl | Name of work
225 | Prepare Drainage Map from Field Survey By Using RTK GPS and Total Station and GIS Software
226 | Inentify Missing link of Khal from Mauza Map
227 | Identify missing link from DEM
228 | Prepare Drainage Map for Print
229 | Detailed Field survey for Drainage and flow Direction
230 | Identify flow Direction
231 | Define Catchment Area for Drainage
232 | Edit Drain database
233 | Prepare Flow Direction Map
234 | Prepare Catchment Area Map and Print
235 | Re Edit by Expert
236 | Re prepare Catchment Map and Print
237 | Finalize Catchment Area and prepare Database
238 | Calculate rainfall data
239 | Link Rainfall data and Analyze
240 | Prepare Drain junction
241 | Analyze Drainage data and prepare Flooding node By Using Pcswmm Software
242 | Find Flooding Area
243 | Finalize Drainage Map
Steps of Drainage Map Preparation

## Slide 20
Delineation of Drainage Catchments for Both Urban & Rural Area
MSDP Area has been Divided into Different Catchments
Total Catchment No : 123
Rural Catchment No : 86
Urban Catchment No : 37
Source : GIS Database

## Slide 22
6th Step of Structure Plan Preparation
Preparation of
Eco Sensitive Land Map

## Slide 23
189 | Prepare Polygone from DEM According to elevation
190 | Reclass Elevation of DEM
191 | Prepare Database
192 | Classify Elevation
193 | Prepare Map and Print
194 | Check on Map
195 | Edit Map and Reclass
196 | Finalize Map and Print
197 | Add Missing link of Drainage From stream line generated from DEM
198 | Classify Waterbody According to Use
199 | Add Classified Waterbody
200 | Demark Eco Sensitive broad Land Zoning and prepare Map
201 | Print Map
202 | Finalize Eco Sensitive broad Land Zoning
Steps of Eco Sensitive Land Map Preparation

## Slide 25
7th Step of Structure Plan Preparation
Preparation of
Ecological Sensitive Map

## Slide 26
Sl | Name of work
260 | Print DEM Map With Grid
261 | Print Physical feature Map With Grid
262 | Print Map of Waterbody With Grid
263 | Prepare different map by Sketching on Different Printed Map at a2 days Workshop
264 | Sketch on printed DEM to find Land Elevation
265 | Sketch on Printed Physical feature Map to find out Existing Urban Area
266 | Sketch on Printed Physical feature Map to find Mature Urban Area
267 | Sketch on Printed Physical feature Map to find Existing Growth Centers
268 | Use Water Policy To find Ecological Zone
269 | Synchronization of all Type of Sketch to find out Ecological Zone
270 | Sketch on Synchronized Map to find Ecological Zone
271 | Scan Map
272 | Transfer Ecological Zone into ARC GIS formate
273 | Add water policy with Ecology Data
274 | Prepare Ecological Sencitive Map and Print
Steps of Ecological Sensitive Map Preparation

## Slide 29
8th Step of Structure Plan Preparation
Preparation of Agricultural Map

## Slide 30
Sl | Name of work
85 | Agriculture Map Prepared from Image
86 | Agriculture Map Verified from PRA with Sub Assistant Agriculture Officer
87 | Edit Agricultural data
88 | Reform and Update Agricultural Data
89 | Varification of Agricultural Map from Agri Office of Mymensingh
90 | Re Update of Agri Database
91 | PrepareCropping Pattern Map and print
92 | Finalization of Agricultural Map
Steps of Agricultural Map Preparation

## Slide 32
Union Name | Crop Pattern (Area in Acre) |  |  |  | 
 | Single Crop | Double Crop | Triple Crop | Grand Total | %
Akua Union | 109.55 | 1470.84 |  | 1580.40 | 4.35
Baera Bhaluka | 196.70 | 327.81 | 152.50 | 677.02 | 1.87
Bhabkhali | 1194.96 | 3346.95 |  | 4541.92 | 12.51
Char Ishwardia Union | 145.80 | 2853.12 | 1107.99 | 4106.92 | 11.32
Char Nilakshmia Union | 79.48 | 2233.65 | 2591.71 | 4904.83 | 13.51
Dapunia Union | 371.15 | 2388.01 | 1637.54 | 4396.70 | 12.11
Ghaagra Union | 471.24 | 2808.74 | 1420.07 | 4700.04 | 12.95
Khagdahar Union | 1409.57 | 1507.65 | 2051.93 | 4969.16 | 13.69
Mymensingh Paurashava | 350.59 | 827.94 | 104.78 | 1283.31 | 3.54
Sirta Union | 431.74 | 3305.71 | 1397.43 | 5134.88 | 14.15
Grand Total | 4760.79 | 21070.42 | 10463.95 | 36295.17 | 100.00
Crop Pattern of MSDP Area (From PRS Session)
There is no triple Crop Land in Akua & Bhabkhali
Highest Agricultural Land : KhagdaharUnion
Lowest Agricultural Land : Baera Union

## Slide 33
9th Step of Structure Plan Preparation
Preparation of Geological Map

## Slide 34
103 | Geological Survey (SPT, Borehole, MT, MSAW)
104 | Geological Survey Checking By MSDP Team
105 | Collection and Analysis of Geological Data
106 | Raster Data Preparation
107 | .shp file Prepared from Raster data
108 | Database Prepare for all type of Geological Survey
109 | Synchronization of all Type of Geological Data
110 | Geological Map Prepared and Print
111 | Explanatory Map prepared from analysis of Geological Data
112 | Height Sensitive Map Prepared from Geological Data
113 | Foundation Depth map Prepare
114 | Soil Layer Map Prepare
115 | Earthquake map Prepare
116 | Earthquake Intensity Map Prepare
117 | Varification of Geological Data from Expart
118 | A 2 Days Workshop on Geological Data and Map
119 | Re-Explanatory Map prepared from analysis of Geological Data
120 | Re Prepare of Height Sensitive Map
121 | Re Prepare Foundation Depth map
122 | Re Prepare Soil Layer Map
123 | Re Varification of Geological Data from Expart
124 | Re Prepare Earthquake map
125 | Re Prepare Earthquake Intensity Map
126 | Finalization of Geological Map
127 | Prepare Earthquake Impact Analysis Map Based on Building Height
128 | Demak Hot spot Zone After Earthquake
Steps of Geological Map Preparation

## Slide 35
Soil Type Map

## Slide 37
10th Step of Structure Plan Preparation
Preparation of
Earthquake Sensitive Map

## Slide 39
11th Step of Structure Plan Preparation
Preparation of
Urban Road Map

## Slide 40
Sl | Name of work | Sl | Name of work
1 | Prepare and Finalize Road Network from Field survey by Using RTK GPS, Total station | 21 | Buffer Road centerline According to Road Type and Lane
2 | Categorization of Road According to Width | 22 | Identify Affected Structure
3 | Buffer all Road for a road network (12ft, 16ft & 20ft width) | 23 | Listing of Affected building By Type & Height
4 | Find out the Structures which are affected due to Road widenning | 24 | Affected Portion has been Identified from GIS Data
5 | Listing of Affected building By Type & Height | 25 | Prepare Map and database for print
6 | Affected Portion has been Identified from GIS Data | 26 | Re-Demarcation and Make decision on road Network System
7 | prepare Map and database for Field survey | 27 | Re adjust Road centerline According to Decision
8 | Map and Database Print for Check from field | 28 | Buffer Road centerline According to Road Type and Lane
9 | Data Check and Additional data has been Collected for Affected building from field Survey | 29 | Re-Identify Affected Structure
10 | Affected Building's Image has been Captured | 30 | Re Listing of Affected building By Type & Height
11 | Database Prepare & Updated | 31 | Re Identify Affected Portion from GIS Data
12 | Database linked with Previous Database | 32 | Re Prepare Map and database for print
13 | Images are linked with the database | 33 | Again new decisions are made on road Network System
14 | prepare Map and database for Print | 34 | Re adjust Road centerline According to Decision
15 | Print Road network Map | 35 | Buffer Road centerline According to Road Type and Lane
16 | Prepare Different Grid For road Network (100m,200m, 250m, 500m) | 36 | ReIdentify Affected Structure
17 | Print Road Network with Grid | 37 | Re Listing of Affected building By Type & Height
18 | Sketch on Printed Road Network Map | 38 | Re Identify Affected Portion from GIS Data
19 | Demarcation and Make decision on road Network System | 39 | Re Prepare Map and database for print
20 | Re adjust Road centerline According to Decision | 40 | Print Map
 |  | 41 | Finalize Road network for Urban Area
Steps of Urban Road Map Preparation

## Slide 41: Categorization of Road
Sl No. | Road Width(m) | Length(M) | Sl No. | Road Width(m) | Length(M) | Sl No. | Road Width(m) | Length(M) | Sl No. | Road Width(m) | Length(M)
1 | 1.64 | 40.66 | 25 | 7.54 | 1361.3 | 49 | 12.14 | 885.56 | 73 | 21.32 | 4116.43
2 | 1.97 | 53.54 | 26 | 7.71 | 649.32 | 50 | 12.3 | 910.21 | 74 | 21.65 | 197.46
3 | 2.62 | 64.7 | 27 | 7.87 | 1198.99 | 51 | 12.46 | 1303.58 | 75 | 22.3 | 1624.59
4 | 3.28 | 4697.58 | 28 | 8.2 | 23300.68 | 52 | 12.79 | 129.41 | 76 | 22.96 | 883.03
5 | 3.61 | 235.06 | 29 | 8.53 | 5527.44 | 53 | 13.12 | 13437.2 | 77 | 23.94 | 1697.39
6 | 3.94 | 9447.65 | 30 | 8.69 | 14.22 | 54 | 13.45 | 662.63 | 78 | 24.6 | 538.43
7 | 4 | 53.39 | 31 | 8.86 | 2351.52 | 55 | 13.78 | 1387.64 | 79 | 24.93 | 10.91
8 | 4.26 | 2088.8 | 32 | 9.02 | 1022.19 | 56 | 13.91 | 298.67 | 80 | 25.75 | 104.4
9 | 4.59 | 1245.72 | 33 | 9.18 | 4829.82 | 57 | 13.94 | 2002.96 | 81 | 26.24 | 4362.42
10 | 4.92 | 18314.8 | 34 | 9.28 | 479.33 | 58 | 14.1 | 507.43 | 82 | 27.06 | 146.21
11 | 5.25 | 7394.48 | 35 | 9.35 | 450.01 | 59 | 14.76 | 2470.32 | 83 | 27.88 | 86.55
12 | 5.41 | 70.87 | 36 | 9.45 | 137.97 | 60 | 15.09 | 328.7 | 84 | 28.21 | 769.14
13 | 5.58 | 1110.94 | 37 | 9.51 | 1875.09 | 61 | 15.42 | 138.62 | 85 | 28.54 | 527.71
14 | 5.9 | 5746.58 | 38 | 9.74 | 79.51 | 62 | 15.74 | 2963.16 | 86 | 28.86 | 375.91
15 | 6.23 | 956.75 | 39 | 9.84 | 49450.47 | 63 | 16.4 | 4658.66 | 87 | 29.52 | 660.47
16 | 6.4 | 59.89 | 40 | 10.17 | 257.79 | 64 | 16.76 | 214.51 | 88 | 31.16 | 13.88
17 | 6.56 | 29596.87 | 41 | 10.33 | 1200.51 | 65 | 17.38 | 909.45 | 89 | 32.8 | 1933.6
18 | 6.72 | 28.54 | 42 | 10.5 | 8151.92 | 66 | 18.04 | 5805.48 | 90 | 34.44 | 313.27
19 | 6.89 | 793.9 | 43 | 10.66 | 83.26 | 67 | 18.37 | 2714.18 | 91 | 36.08 | 1527.5
20 | 7.02 | 65.18 | 44 | 10.82 | 3460.76 | 68 | 19.02 | 475.92 | 92 | 40.34 | 327.99
21 | 7.05 | 151.71 | 45 | 10.99 | 270.88 | 69 | 19.19 | 591.57 | 93 | 49.2 | 45.27
22 | 7.12 | 153.73 | 46 | 11.15 | 1328.86 | 70 | 19.68 | 2189.89 | 94 | 52.48 | 1598.2
23 | 7.22 | 6434.38 | 47 | 11.48 | 14695.92 | 71 | 20.66 | 63.27 | 95 | 60.68 | 154.29
24 | 7.38 | 72.46 | 48 | 11.81 | 3466.79 | 72 | 20.99 | 166.59 | 96 | 65.6 | 327.01
From the Road Data 96 type of Road width has been Identified
Source : GIS Database

## Slide 42
Status of Road Type By Length and Area
Road Type | Road Area(Acre)
Tertiary C(<12ft) | 138.78
Tertiary A(>=18<30ft) | 44.03
Tertiary B(>=12<18ft) | 31.79
Access(>=30<39ft) | 11.33
Primary(>=45ft) | 8.02
Secondary(>=39<45ft) | 1.02
Total | 234.96
Chart: Condition of Road Type By Area
| Tertiary C(<12ft) | Tertiary A(>=18<30ft) | Tertiary B(>=12<18ft) | Access(>=30<39ft) | Primary(>=45ft) | Secondary(>=39<45ft)
% | 59.0639 | 18.74 | 13.5284 | 4.8215 | 3.4115 | 0.4346
Road Type | Length(M)
Tertiary C | 214551.22
Tertiary B | 33208.71
Tertiary A | 28107.96
Access | 3788.26
Primary | 2096.31
Secondary | 327.99
Total | 282080.44
Chart: Status of Road By Length
| Tertiary C | Tertiary B | Tertiary A | Access | Primary | Secondary
Length(M) | 214551.2171 | 33208.7087 | 28107.9597 | 3788.2565 | 2096.309 | 327.9933

## Slide 43
Sketch on Tracing while Road Designing

## Slide 44
Design and Calculation of Structures

## Slide 45
12th Step of Structure Plan Preparation
Preparation of
Regional Road Map

## Slide 46
Sl | Name of work
1 | Prepare Physical Feature Map for MSDP Area
2 | Sketch on Printed Map for Regional Road Network
3 | Scan Map
4 | Geo-reference Map
5 | Edit and Prepare Road network
6 | Print Prepared Road Network
7 | Re sketch on Prited Road Network
8 | Scan Map
9 | Georeference Map
10 | Re Edit and Prepare Road network
11 | Print Re edited Network on Classification of Elevation
12 | Re suffle Road Network
13 | Define Type of Road and Define Width of road
14 | Buffer Road centerline According to Road Type and Lane
15 | Find out the Structures which are affected due to Road widenning
16 | Listing of Affected building By Type & Height
17 | Affected Portion has been Identified from GIS Data
18 | Prepare Database for Regional Road network
19 | Database Varified with Expert opinion
20 | Finalize Regional Road network for MSDP Area
Steps of Regional Road Design Map Preparation

## Slide 47
Sketch on Tracing while Designing Regional Road

## Slide 49
13th Step of Structure Plan Preparation
Preparation of
Growth Center Map

## Slide 50
Sl | Name of work
1 | Identification of Growth Center
2 | Prepare growth center Map
3 | Add Forshore with Road from Ecological Zone
4 | Prepare Map with Road Network and Ecological Zone
5 | Print Map
6 | Sketch on Map for Designing Growth Center
7 | Scan Map
8 | Georeference Map
9 | Edit Road At Growth Center
10 | Buffer Road centerline According to Road Type and Lane
11 | Find out the Structures which are affected due to Road widenning
12 | Listing of Affected building By Type & Height
13 | Affected Portion has been Identified from GIS Data
14 | Prepare Database for Road network
15 | Database Varified with Expert opinion
16 | Finalize Road network at growth Centers for MSDP Area
Steps of Growth Center Design Map Preparation

## Slide 53
13th Step of Structure Plan Preparation
Preparation of
Fire Escape Map

## Slide 54
Sl | Name of work
1 | Prepare Physical Feature Map of Municipality For Fire Service and civil Difence
2 | Map Print
3 | Sketch Drawn By Fire Service and civil Defense on Map at PRA
4 | Data Collected from Fire Service and civil Difence through PRA
5 | Scan Map
6 | Georeference Map
7 | Prepare & Update Database for fire escape Route
8 | Prepare fire incidence .shp file and database
9 | Prepare Map and Print
10 | Analyze Fire Incidence Data and Find out Hot Spot
11 | Prepare Escape Route
12 | Finalize Fire Escape Route
Steps of Fire escape Map Preparation

## Slide 55
Fire Escape Road of Municipality Proposed By
Fire Service & Civil Defense
Fire Escape Map has been Prepared from PRA Session Which was held with Fire Service & Civil Defense
Source : GIS Database

## Slide 56
14th Step of Structure Plan Preparation
Preparation of
Crime Map

## Slide 57
Sl | Name of work
1 | Collect Crime Data from Thana
2 | Prepare .shp file for Crime Data
3 | Analyze Data
4 | Prepare Crime hot Zone Map & Database
Steps of Crime Map Preparation

## Slide 58
Collection of Last five years Data
Total Incidence 380
Fire Incidence Data Collection and Database Preparation
Source : GIS Database

## Slide 59
15th Step of Structure Plan Preparation
Preparation of
Network Analysis Map

## Slide 60
Sl | Name of work
1 | Sample Data Collected from Socio Economic Survey for Educational Network Analysis
2 | Prepare .shp file for Primary Educational Institute Analysis
3 | Analyze and prepare Map
4 | Prepare .shp file for Secondary Educational Institute Analysis
5 | Analyze and prepare Map
6 | Prepare .shp file for Higher Secondary Educational Institute Analysis
7 | Analyze and prepare Map
8 | Prepare .shp file for University Analysis
9 | Analyze and prepare Map
10 | Sample Data Collected from Socio Economic Survey for Bazaar Network Analysis
11 | Prepare .shp file for Bazar Analysis
12 | Analyze and prepare Map
13 | Sample Data Collected from Socio Economic Survey for Health Facility Network Analysis
14 | Prepare .shp file for Health Facilities Analysis
15 | Analyze and prepare Map
16 | Sample Data Collected from Socio Economic Survey for Religious Facility Network Analysis
17 | Prepare .shp file for Religious Facilities Analysis
18 | Analyze and prepare Map
Steps of Network Analysis Map Preparation

## Slide 61
Analytical Example of University

## Slide 62
16th Step of Structure Plan Preparation
Preparation of
Draft Structure Plan Map

## Slide 63
Sl | Name of work
1 | Proposals of Draft Structure Plan were Drafted Synchronizing all of the data (Drainage, Road, land elevation, Geology, Landuse, PRA Data, Network Analysis)
2 | Draft Structure Plan Map Prepared
3 | Print of Draft Structure Plan Map
4 | In house Dialogue of Professionals has been performed on this Draft Plan
5 | Edit of Structure Plan Proposals
6 | Draft Structure Plan Map Prepared
7 | Print of Draft Structure Plan Map
8 | Again In house Dialogue of Professionals has been performed on this Draft Plan
9 | Edit of Structure Plan Proposals
10 | Prepare Structure Plan Map
Steps of Draft Structure Plan Map Preparation

## Slide 64
Conceptual Structure Plan

## Slide 66
Special Achievement

## Slide 67
Thanks