- Introduction

1.1	Background Information

In course of progress of the project, the Project Management Team may encounter technical/administrative problems or sectoral conflicts may arise in taking planning decisions, which would require solving. Keeping this view in mind, a Technical Management Committee (TMC) has been formed by the Ministry of Housing and Public Works (MoHPW) for oversee the activities of Mymensingh Strategic Development (MSDP) Project. The committee is chaired by the Joint Secretary (Development), MoHPW and consisting of 15 (fifteen) members. The first meeting of the Committee was held 25 May, 2013 at Mymensingh. Details of the meeting are described in the following sub-sections.

1.2 Formation of Technical Management Committee (TMC)

According to the MOU, UDD has initiated a planning package for Mymensingh municipality and its surrounding rural areas for mainstreaming disaster risk reduction in land use planning and management. As part of implementation of the planning package, a Technical Management Committee (TMC) has been formed by the Ministry of Housing and Public works through a gazette notification vide memo no. 25.03.0000.014.00.016.11.260 dated 22.04.2013 consisting of 15 (fifteen) members chaired by the Joint Secretary (Development), Ministry of Housing and Public Works for effective implementation of the project.  The Gazette notification for the formation of TMC is given in Appendix-I.

1.3 Scope of Work of TMC

According to the gazette notification, the scope of work of the TMC is as follows:

- Identify the administrative/technical problems of the project and take necessary action to solve the problems.

- Co-opt new member in the committee (if necessary).

- Arrange meeting during implementation of the project.

- Identify sectoral conflicts at the time of taking planning decisions (if any) and solve the problems.

2. The 1st Meeting of the TMC

After formation of TMC, the first meeting of the Committee was held on 25 May 2013 at Mymensingh. The meeting was chaired by Mr. S. M. Arif-ur-Rahman, Joint Secretary (Development), Ministry of Housing and Public Works. Venue of the meeting was seminar room of SPONDON, Amirabad Residential Area, Maskanda, Mymensingh. Among fifteen members eleven members including one more nominated member from Khulna University attended the meeting. Details of the meeting are described in the foregoing sub-sections. It is to be noted here that if any confusion arises about the contents of the report, then the minutes of the meeting, which is attached in the Appendix-II, would be used as reference and be treated as the valid.

2.1 Inauguration Session of the Meeting

The meeting started with the recitation from the Holy Quran. Honorable Chairman welcomed the members of the committee, who attended the meeting. In his welcome speech, the chairman expressed his heart felt gratitude to CDMP and UDD for undertaking such project like “Mainstreaming Disaster Risk Reduction in Land Use Planning” in Bangladesh for the first time. Then, he requested Dr. K. Z. Hossain Taufique, Project Director (PD), to give an overall description about the project.

2.2 Describing the Project Background and Progress of the Project

As requested by the Chairman, the PD explained the conceptual and structural formation of the project along with progress of the project activity and other relevant issues. Decision of undertaking a development planning project is a logical and timely decision as present development trend of Dhaka is extending from Gazipur to Mymensingh. Besides, from the geological point of view, Mymensingh is at potential risk of earthquake. Hence, integrating the possible risk of disaster and seismic risk in particular into development planning process is a revolutionary decision in the history of physical planning in Bangladesh.

The PD also stated that Disaster Risk Reduction (DRR) is going to be integrated in land use planning for the first time in Bangladesh. A Planning module would be developed following the planning process of the whole planning package, which would be used as a model in preparation of disaster Risk sensitive land use plan. He also presented 4 (four) reports on different events of the project activities including (i) Inception Report, (ii) Report Children Art Competition and Workshop, (iii) Report on Rural PRA Sessions; and (iv) Report on Urban PRA Sessions for review by the members of TMC. The members of TMC opine that the reports are reasonably acceptable.

Then Dr. Taufique requested Mr. Ahsan Habib, Assistant planner, to explain the present status and progress of Physical Feature Survey Checking through Power Point Presentation and other Consultants to explain their own activities as well.

2.3 Explanation of Different Activities and Events of MSDP Project by Project Personnel and Consultants

Mr. Ahsan Habib,   Assistant planner, UDD explained The physical feature Survey data Update activities including identification of holding no, and floor based uses of difference physical feature in detail on the TMC meeting.

Mr. Shahin Ahmed, on behalf of Decode Ltd. and Geomark presented a report on Mouza Map Digitization and Geo-referencing.

Mr. Tamzidul Islam, on behalf of Decode-Bestway- Geomark Ltd. discussed  about benefit of using 3-D GIS in Planning process through Photogrammety and finding from analysis of Sample Questionnaire Survey, which were received from mail Questionnaire.

2.4. Discussion by the TMC Members during Meeting

Discussion on Various Project Components by the members of TMC during meeting is discussion below:

2.4.1. Discussion by the Representative from Geological Survey of Bangladesh (GSB)

Mr. A. T. M. Asaduzzaman, Director, GSB welcomed the MSDP Project due to timely initiation of assessing seismic rick from the results of geo-physical survey with the assistance from CDMP and incorporating it into land use planning. He stated that impact of Dhaka-Mymensingh connecting High on Mymensingh should be reflected with due importance into the development planning considering the highway as “Development Corridor”. He explained the process of Geological Survey for determining geo-physical structure through `bore-hole’ and impact of earthquake on building structure. He told that, at present GSB is using three-Dimensional Geological Model. It is possible to determine three dimensional geo-physical structure of soil more precisely through 3-D model. As an example, he stated that at Aftabnagar, structural intervention equivalent to 16-storey building is required to reach sub soil through piling. He also told that it is not possible to forecast the geo-physical structure of Mumensingh through the Engineering Geology with only 20 numbers of bore-holes, because it is required to make bore-hole at 250m internal for collecting three dimensional data to prepare “micro-zonation” map. In fact, it is also difficult to prepare a three-dimensional geo-physical map with the results from bore-holes at 250m. interval.  In response to the proposed of conducting geological survey with the fund allocated with MSDP project for the said survey. Mr. Asad said that according to its “Charter of Duties”, GSB cannot accept money from any organization for conducting Geological Survey. In this respect, GSB can assign their officers to supervise the survey work, if UDD conducts geological survey. He added that no limit should be given for the depth of bore-hole in case of identification of Geo-physical hazard. Boring to be continued until target layer is reached. Otherwise, risk estimation may lead to deceptive and fallacions result.

2.4.2. Discussion by the Representative from CDMP

Dr. Nurul Islam, Urban Disaster Risk Reduction Specialist, CDMP, emphasized on undertaking planning initiative in the areas of higher risk of disasters. He also told that initiative of incorporating the risk of different disasters into development planning of Mymensingh has a great significance, because seismic risk was not assessed in preparation of Detailed Area Plan for RAJUK. He explained the role of CDMP in this respect. He also told that most of the incidents of urban fire hazard occurred from the electric short circuit in the buildings. So, he requested to incorporate the issue of electric supply line in assessing the risk of urban disaster.

2.4.3. Discussion by the Representative from Asian Disaster Preparedness Center (ADPC)

Mr. Anisur Rahman, Senior Project Manager, ADPC, told about their activities that only the seismic risk and its impact is to addressed by ADPC for MSDP Project, according to TOR. He also told that `Z’ Value i.e., elevation of land from mean sea level (MSL) has not been included into GIS database of Physical Feature Survey. GIS Database Combining with `Z’ value would be supplied to UDD very soon. Moreover, ADPC would upgrade the database according to the findings from Physical Feature Survey Checking by UDD.

2.2.4. Discussion by the Representative from Urban and Rural Planning Discipline, Khulna University

Professor Dr. Shamim-Mahbubul Haque, Urban and Rural Planning Discipline, Khulna University emphasized on reviewing “Draft Urban Policy, 2012” thoroughly prior to prepare structure plan and requested MSDP Project Team Members to incorporate the provisions made under “Standing Order on Disaster” (SOD) in case of integrating the risk of disaster into planning Package. Asked the MSDP project personnel that how the Pucca, Semi-pucca and Kutcha structures been defined in case of Physical feature Survey. He stated that quality of data is the pre-requisite for preparing an acceptable plan. On the basis of analysis of such data a draft master would be prepared and lastly, the planning package is to be finalized on the basis of comments from all the stakeholders.

2.2.5. Discussion from Another Representative from Urban and Rural Planning Discipline, Khulna University.

Professor Dr. Mostafa Saowar, Urban and Rural planning discipline, Khulna University, requested to consider the law under the provisions of which the buildings would be identified as high, medium and Low vulnerable and are to be enforced in case of implementation of the plan. In case of integrating DRR into land use planning, he said that the resource, which is required to save a person, it is possible to rehabilitate many persons by using the same resource. He also told that in case of population projection, three deferent growth rates including high, medium and lows has been used. He requested to consider other theoretical basis of population projection in estimating future population for the project area. As an inhabitant of Mymensingh town, Dr. Sarowar urged that there is no tradition of social relation specially marriage of the people of mainland with that of char land. In this connection, how far the initiative of diverting development trend on the other bank of the river Brahmaputra would be fruitful. He requested to consider the prevailing social norms for preparing the plan for Mymensingh.

2.2.6 Discussion by the Representative from Urban and Regional Department, Bangladesh University of Engineering and Technology (BUET)

Professor Dr. Mohammad Shakil Akter, Urban and Regional Department, (BUET), in his discussion about the project told that it is reveled from a research on Sirajganj conducted by researcher of Jahangirnagar University that usually a person do  not want to stay in char land for more than seven years, which should be considered in preparing plan for Mymensingh. He also requested to consider the issue of migration along with using mathematical methods of population projection for forecasting population for the project period. In response to his question, who would estimate the probability of hazard and prepare risk-sensitive map, the project director, replied that UDD would conduct the activity with the technical assistance from ADPC.

2.2.7 Discussion by the Representative from the Ministry of Disaster Management and Relief

Md. Monirul Islam, Executive Engineer. Ministry of Disaster Management and Relief, requested to incorporate all on going and approved future projects of different sectoral agencies within the project area into the plan.

2.2.8 Discussion by the Representative from the Mymensingh Paurashava

Md. Rafiqul Islam Bhuiyan, Executive Engineer, Mymensingh Paurashava, stated that the Pourashava in under tremendous pressure from the local people in cast of integrating disaster risk reduction into planning. He also requested CDMP to provide the data to the paurashava after classification of vulnerable structures.

2.2.9 Discussion by the Representative from the Upazila Nirbahi Officer

Md. Dewan Nurul Huda, P.I.O, requested to make provision of two bridges on the river Brahmaputra to bring rural area of the project area into the urbanization process.

3. Problem faced during Implementation of the Project

At this stage, the chairman requested the PD to discauss the problem, which he faced in implementing the project.

In this connection, Dr. Taufique said that a close collaboration is essential among CDMP-ADPC-GSB-UDD to integrate DRR in urban planning as the issue of Geo-Informatics is a new phenomenon to MSDP Project Team. So, for integrating DRR in urban planning, mutual cooperation among these from agencies is essential. According to the MOU between UDD and CDMP, two GIS training programmes at middle and upper level would be arranged by CDMP. It is expected that CDMP would arrange the training programmes as soon as the database of MSDP would be finalized.

The most crucial fact is that the Project Director, MSDP Project has been transferred/posted by the Government of Bangladesh to Rajdhani Unnayan Kartipakkha (RAJUK) on the position of Director, Team Planning Section. So, it is very difficult on his part to implement the project properly. So, a full-time Project Director is essential to implement the project. Besides, the UDD authority has issued  a “Show Cause” notice with the two Project Managers of the Project, namely,  Mr. Ahmed Aktaruzzaman, Senior Planner, UDD and Mr. Quazi Md. Fazlul Haque, Senior Planner, UDD on matter of administrative issues. This has created extreme psychological pressure on them. As a result, it has become difficult for them to implement the project effectively. So, this issue should be solved immediately for effective implementation of the project.

He told that the website of the project would be operative by the end of June, 2013. But it is required to periodical publication on MSDP project activities. But there is no budgetary allocation for the said purpose. CDMP may provide financial assistance in this respect. According to MOU, there is a provision of renting microbus in the agreement. A tender was called for renting the “microbus”. But, it could be rented due to increase in market price. According to the “Financial Agreement” signed with CDMP, there is allocation of Taka 6.66 lac for renting microbus. But the lowest tender quoted the estimated price of Taka 10.00 lac (excluding VAT and Tax) in an open tender. So, due to this reason, the project team members face difficulty in implementing the project. Hence, CDMP is to be requested to increase the budgetary allocation for renting microbus.

Rent period for the “Project Office” at Maskanda should be increased for the period of additional 06 (Six) months for successful implementation of the project.

Dr. Nurul Islam, Urban Disaster Risk Reduction Specialist, MSDP urged that the estimated cost for signing the “Financial Agreement” has been prepared by UDD. Hence, UDD was supposed to consider these matters and preparing the estimated cost. In spite of this, he requested UDD to send a formal letter to CDMP relating to the financial matters discussed above.

4. Concluding Speech by the Chairman

Mr. A. S. M. Arif-ur-Rahman, Joint Secretary (Development), Ministry of Housing and public Works and Chairman, Technical Management Committee (TMC) conveyed  his heartiest thanks to the members of TMC, who attended the meeting for their active and spontaneous participation and lively discussion on the project components and activities.

He suggested the MSDP team to consider the use of the buildings as approved by the paurashava authority and compare it with the usage that would be found from the survey. He also proposed to co-opt the Assistant Commissioner, Land, Mymensingh Sadar Upazila in the TMC, as the cadastral (mouza) map and information related to khas land are kept under his custody. At the same time, he also proposed to co-opt a representative from Bangladesh Fire Service and Civil Defense (BFSCD), as BFSCD deals with urban disaster response. Dr. Shakil seconded him on the issue and the rest of the members were unanimous on the point. Then the Chairmen, asked the PD to take necessary official actions on co-opting those members into the TMC of MSDP Project.

Besides, the also proposed to co-opt the other two members who are nominated by concerned authorities for the TMC, who already attending and participating the meeting, from the Urban and Rural Planning Discipline of Khulna University and also from the Geology Department of  Dhaka University into the TMC. All the members of the TMC were also unanimous on the matter.

Above all, he emphasized on completing the project duly and to make it visible to everyone. He requested the MSDP Project Team members to arrange the meeting of TMC in every on (four) months interval. Then he closed the meeting with thanks to TMC members and orginisers.

5. Miscellaneous

During the interval of the meeting, Chairman of TMC distributed the certificates, crests of MSDP Project and books as prizes among the 09 (nine) winners of Children Art Competition in 03 (three)  different groups and also distributed the same among the 05 (five) winners of Essay Competition at college level as well. It is to be noted here that Children Art Competition was arranged for three age groups entitled “(i) My House, (ii) My Surrounding, and (iii) My Town Mymensingh” at the “Shilpacharga Jainul Abedin Shangrahashala” Auditorium. Besides, an Essay Competition entitled “According to My Vision Mymensingh Town in the Year 2031” was also arranged at the same time.

The Project Director, MSDP requested CDMP through the Chairman, TMC to provide financial assistance to the two Project Managers of MSDP Project, who are continuing Ph. D Programme by using the data and information of MSDP Project.

Dr. Nurul Islam, Urban Disaster Risk Reduction Specialist, CDMP requested to send a formal letter to CDMP relating to the issue of extending assistance to the Ph. D Programme. He assured to provide all sort of assistance in this respect.

6. Decision Taken in the Meeting

The following decisions were taken in the meeting after detailed discussion on the project components and activities.

6.1 Decisions

1. Assistant Commissioner, Land, Mymensingh Sadar Upazila and a representative from BFSCD would be co-opted in the TMC, after getting necessary approval from their competent authority. Besides two more nominated representatives from Urban and Rural Planning Discipline of Khulna University and Geology Department of Dhaka University as well, who attended the meeting, were also co-opted in the TMC.

2. The Executive Engineer, Mymensingh Pourashava would supply the both list of buildings and plans as well, which already been approved by the paurashava, to MSDP team.

3. CDMP would provide all documents and information relating to software license; and also Auto CAD Software as per agreement to UDD with least possible time to speed up the progress of the project activities.

4. CDMP would consider the extension of rent of “Project Office” at Maskanda for 06(Six) months more.

5. CDMP would consider for increasing the amount of approved money which would be required for rent of “Microbus” due to increase the price in market.

6. The four reports, which were presented in the meeting, were accepted by all the members of TMC, who attended the meeting.

7. The meeting of TMC may be arranged in every members 04(Four) months interval depending on the progress of the project implementation if necessary.

8. The next meeting of TMC would be held on the last week of September, 2013 at the Seminar Room of Urban Development Directorate (UDD) in Dhaka.

Photo: A Glimpse of the TMC Meeting

| Photo 01: Mr. A. S. M. Arif-ur-Rahman, Joint Secretary (Dev), MoHPW & The Chairman, TMC |  | Photo 02: The 1st Meeting, TMC |
| --- | --- | --- |
| Photo 03: Discussion by the Urban Disaster Risk Reduction Specialist, CDMP |  | Photo 04: Discussion by the director, Geological survey of Bangladesh (GSB) |
| Photo 05:Prize Distribution among Winners |  | Photo 06:Prize Distribution among Winners |